## OKRs
Objective | Key Result | Priority | Status | Score | Eng Owner | PM Owner | links | Updates (use comments) | Scoring Criteria
Modernize ML Platform to power suite-wide discovery | 10% lift in engagement on new ML feed | p1 | Completed | 0.8 |  |  |  |  | 0.7 = 10%, 1.0 = 20%, linear
| >75% of legacy signals plumbed into new architecture | p2 | On Track | 0.4 |  |  |  |  | There are 3 legacy signals: realtime, user, group, network. We want at least 3 out of the 4
| Feedback received from at least 3 customers on muting posts | p2 | On Track | [5 empty] | Binary
Delight internal stakeholders with fast, seamless analytics
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why we think we’re on-track: 4 days left of planned work before bugbash. Currently tracking ahead of schedule by 3 days. Reply: Why we’re think we’re on track: Bug bash successful, issues triaged. Beginning dogfood Monday. Reply: At risk: Major issue identified under Windows / IE11. Working on a mitiigation plan. Reply: Agreed to drop IE11 support. On track for release.